## Instructions
How to Use This Template
Step 1: List Key Activities | Focus on activities where confusion creates pain. Start with 10-15 activities that cause 80% of confusion.
Step 2: Assign RACI | R = Does the work ¦ A = Owns outcome (only ONE per activity) ¦ C = Provides input ¦ I = Kept updated
Step 3: Analyze Gaps | Check for red flags: multiple A's, no A, bottlenecks, overloaded roles
Step 4: Test It | Run scenarios: 'Who handles X?' If unclear, refine the matrix.
Step 5: Make It Visible | Post in team workspace, include in onboarding, reference in working agreements.
Step 6: Keep It Current | Review quarterly. Update when team changes, new work types emerge, or AI changes workflows.
Tips
• Time-box debates: 3 minutes max per activity, then move on
• Use real examples to ground discussions
• Default to clarity over perfection
• The matrix clarifies accountability, not permission—anyone can help with anything
From Agile Meets AI: A Pragmatic Guide for Modern Teams by Sheila Eckert
Download more resources at thesheilaverse.com/book-companion

## RACI Template
RACI Matrix Template
R = Responsible (Does the work) ¦ A = Accountable (Owns the outcome) ¦ C = Consulted (Provides input) ¦ I = Informed (Kept updated)
Category | Activity | Product Owner | Scrum Master | Developers | Stakeholders | Tech Lead | Notes
Product & Planning | Product vision and strategy | A/R | I | C | C | C | PO owns product direction
| Backlog prioritization | A/R | C | C | I | C
| Acceptance criteria definition | A | I | R | C |  | Dev writes, PO approves
| Release planning | A | R | C | I | C
Delivery & Execution | Sprint planning | A | R | A/R | I | C | Dual accountability
| Daily standup |  | C | R |  |  | Team-owned ceremony
| Code development | I |  | A/R |  | C
| Code review |  |  | A/R |  | C
| Deployment decisions | C | I | A/R | I | C
Technical | Architecture decisions | C | I | C | I | A/R
| Technical debt prioritization | C |  | R |  | A
Customer & Stakeholder | Customer interviews | A/R |  | C | I
| Sprint review facilitation | R | R | R | C |  | Shared responsibility
Team Health | Retrospective facilitation | C | A/R | R |  |  | Can rotate
| Conflict resolution | C | A/R | R
AI & Innovation | AI tool evaluation | C | I | R | I | A | Within guardrails
| AI output validation |  |  | A/R |  | C
YOUR ACTIVITIES

## AI Activities
AI-Related RACI Activities
Activity | Product Owner | Developers | Tech Lead | AI Specialist | Leadership | Notes
AI tool evaluation and approval | C | R | A | R | I | Teams propose, Tech Lead approves
AI coding assistant guidelines | I | C | A/R | C | I
AI output validation standards | I | A/R | C | C
Prompt engineering best practices | I | R | C | A |  | AI Specialist owns standards
AI-generated code review |  | A/R | C | C |  | Same as regular code review
AI experiment tracking | I | R | C | A | I
AI ethics review | C | C | C | R | A | Leadership accountable
Bias detection and mitigation | C | R | C | A | I
AI security and data privacy | I | C | A | R | I
AI cost management | C | I | R | C | A
AI training and capability building | I | R | C | A | C

## Health Check
RACI Health Check
Red Flags to Watch For
☐ | Unclear Ownership | Activity has no 'A' or multiple 'A' assignments
☐ | Decision Paralysis | Too many 'C' assignments on an activity
☐ | Approval Bottleneck | One person is 'C' on too many items
☐ | Information Hoarder | Too many 'I' assignments causing noise
☐ | Overloaded Ownership | One person is 'A' for too many activities
☐ | Phantom Responsible | Someone marked 'R' has no capacity
Healthy Patterns
☐ | Clear Accountability | Every activity has exactly one 'A'
☐ | Balanced Workload | No one is 'A' for more than 5-7 critical activities
☐ | Minimal Consultation | 'C' only where input genuinely changes decisions
☐ | Effective Info Sharing | 'I' only for people who need to know and will act
☐ | Decision Speed | Fewer than 3 people involved in most decisions