## Instructions
How to Use These Templates
1. Choose the right template | Select the tab that matches the analysis you want to run.
2. Export or enter your data | Export from Jira/tools, or manually enter data following the example format.
3. Replace example data | Delete the green example rows and add your own data.
4. Copy for AI analysis | Select your data (including headers), copy, and paste into the AI prompt.
Data Export Tips by Tool
Jira | Use Filters > Export > Excel. Customize columns before export to match template.
Azure DevOps | Use Queries > Export to CSV. Convert to Excel if needed.
Trello | Use Power-Ups or third-party tools to export card data.
Manual Tracking | If your tool doesn't export what you need, manually log for 2-4 weeks.
Template Tabs
Velocity | Sprint-by-sprint committed vs completed points with team context.
Lead Time | Time from item creation to completion, by class of service.
Cycle Time | Time in each workflow stage to identify bottlenecks.
Defects | Production bugs with root cause categories for pattern analysis.
NPS Feedback | Customer scores and comments for theme extraction.
Retrospective Notes | Categorized retro notes across multiple sprints.
From Agile Meets AI | thesheilaverse.com/book-companion

## Retrospective Notes
Retrospective Notes Template
Copy notes from each retrospective. Include date and category (What went well, What didn't, Actions).
Date | Category | Note
2024-01-19 | Went Well | Pair programming on complex features reduced bugs significantly
2024-01-19 | Went Well | New standup format keeps meetings under 15 minutes
2024-01-19 | Didn't Go Well | Too many meetings mid-sprint broke focus
2024-01-19 | Didn't Go Well | Requirements for PROJ-103 changed twice after sprint started
2024-01-19 | Action | Block 2-hour focus time each morning - no meetings
2024-02-02 | Went Well | Focus time experiment working - team feels more productive
2024-02-02 | Didn't Go Well | Still getting pulled into production support too often
2024-02-02 | Didn't Go Well | Code reviews taking too long - items sitting for 2+ days
2024-02-02 | Action | Implement review SLA - 24 hour max turnaround
2024-02-02 | Action | Create on-call rotation to protect sprint work
YOUR DATA BELOW:

## Velocity
Velocity Data Template
Export from Jira or enter manually. Include context notes for meaningful analysis.
Sprint | Start Date | End Date | Committed Points | Completed Points | Team Size | Notes
Sprint 23 | 2024-01-08 | 2024-01-19 | 34 | 31 | 7
Sprint 24 | 2024-01-22 | 2024-02-02 | 32 | 35 | 7.5 | Added 1 dev mid-sprint
Sprint 25 | 2024-02-05 | 2024-02-16 | 36 | 28 | 5 | 2 team members on PTO
Sprint 26 | 2024-02-19 | 2024-03-01 | 30 | 32 | 7
Sprint 27 | 2024-03-04 | 2024-03-15 | 33 | 30 | 7 | Production incident
YOUR DATA BELOW:

## Lead Time
Lead Time Data Template
Class of Service: Expedite, Fixed Date, Standard, Intangible. Created = entered backlog, Started = work began.
Item ID | Title | Type | Class of Service | Created Date | Started Date | Completed Date | Size (Points)
PROJ-101 | User login feature | Story | Standard | 2024-01-05 | 2024-01-10 | 2024-01-18 | 5
PROJ-102 | Critical security fix | Bug | Expedite | 2024-01-12 | 2024-01-12 | 2024-01-13 | 2
PROJ-103 | Dashboard redesign | Story | Standard | 2024-01-08 | 2024-01-15 | 2024-01-26 | 8
PROJ-104 | Compliance update | Story | Fixed Date | 2024-01-02 | 2024-01-20 | 2024-01-31 | 3
PROJ-105 | Tech debt cleanup | Task | Intangible | 2024-01-10 | 2024-01-22 | 2024-02-05 | 5
YOUR DATA BELOW:

## Cycle Time
Cycle Time Data Template
Track time in each workflow stage. Adjust column names to match your workflow stages.
Item ID | Title | Size | Days in Backlog | Days in Progress | Days in Review | Days in Testing | Days in Deploy Queue | Total Cycle Time
PROJ-101 | User login feature | 5 | 0 | 3 | 1 | 2 | 0.5 | 6.5
PROJ-102 | Critical security fix | 2 | 0 | 0.5 | 0.25 | 0.25 | 0 | 1
PROJ-103 | Dashboard redesign | 8 | 0 | 5 | 2 | 3 | 1 | 11
PROJ-104 | Compliance update | 3 | 0 | 2 | 1 | 1 | 0.5 | 4.5
PROJ-105 | API integration | 5 | 0 | 3 | 2 | 2 | 0.5 | 7.5
YOUR DATA BELOW:

## Defects
Escaped Defects Data Template
Root Cause Categories: Requirements Gap, Testing Gap, Code Error, Environment Issue, Integration Issue
Defect ID | Date Found | Severity | Component/Area | Root Cause Category | Related Feature | Sprint Released | Description
BUG-201 | 2024-01-20 | High | Authentication | Requirements Gap | Login Feature | Sprint 23 | Password reset link expires too quickly
BUG-202 | 2024-01-25 | Medium | Dashboard | Testing Gap | Dashboard Redesign | Sprint 24 | Charts don't render on mobile
BUG-203 | 2024-02-01 | Low | Reports | Code Error | Report Export | Sprint 24 | CSV export missing header row
BUG-204 | 2024-02-05 | Critical | Payments | Environment Issue | Checkout Flow | Sprint 25 | Payment fails in production only
BUG-205 | 2024-02-10 | Medium | Authentication | Requirements Gap | SSO Integration | Sprint 25 | SSO timeout too short
YOUR DATA BELOW:

## NPS Feedback
NPS Feedback Data Template
Include customer segment and tenure for richer analysis. Promoters: 9-10, Passives: 7-8, Detractors: 0-6
Response Date | NPS Score | Customer Segment | Account Age (months) | Verbatim Comment
2024-01-15 | 9 | Enterprise | 24 | Love the new dashboard. Finally easy to see all our data in one place.
2024-01-16 | 6 | SMB | 6 | Too expensive for what we get. Support is slow to respond.
2024-01-18 | 10 | Enterprise | 36 | Best tool we've used. The API integration saved us weeks of work.
2024-01-20 | 7 | SMB | 12 | Good product but the mobile app needs work. Hard to use on the go.
2024-01-22 | 4 | Mid-Market | 3 | Confusing interface. Took forever to figure out basic features.
2024-01-25 | 8 | Enterprise | 18 | Solid product. Would be a 10 if reporting was more customizable.
YOUR DATA BELOW: